## Failed TCs - Create Form
Test Case Id | Test Plan Id | TC # | Platform | Sub Module Features | Action | Test Mode | Created By | Test Case Type | Pre Condition | Test Case Description | Steps | Expected Result | Conditions / Formula / Query | Actual Result | Pass/Fail | Executed By | Date Execution | Remarks | Developer Status | Developer Remark | Retesting(Pass/Fail) | Execute By & Date | Remark
TCM_dKosh_General_SMF1_001_001 | TP_dKosh_General_SMF1_001 | 1 | Web, Mobile | General | Create Form | M | Ankit | UI |  | Verify, Caption, Placeholder, Control type and default value of 'Form Name' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Allowed Duration' field. | Caption : Form Name Place Holder : -- Control Type : Text Default Value : -- |  | Different caption and place holder is not defined in requirement. | Fail | Ankit | 2019-11-14 |  | Resolve |  | Pass | Jaikishan (3 Dec) | Form name changes to "Name" in requirement sheet.
TCM_dKosh_General_SMF1_001_003 | TP_dKosh_General_SMF1_001 | 3 | Web, Mobile | General | Create Form | M | Ankit | Validation |  | Verify, Name field data validation (Min and Max length) | 1. Go to manage form list. 2. Click on plus icon. 3. Enter data in the Name field. | db length should be 100. |  | Should accept max 100 character | Fail | Ankit | 2019-11-14 |  | Resolve |  | Pass | Jaikishan (3 Dec) | But it should stop upto 25 character
TCM_dKosh_General_SMF1_001_006 | TP_dKosh_General_SMF1_001 | 6 | Web, Mobile | General | Create Form | M | Ankit | UI |  | Verify, Caption, Placeholder, Control type and default value of 'Short Name' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Allowed Duration' field. | Caption : Short Name Place Holder : -- Control Type : Text Default Value : -- |  | Different caption and place holder is not defined in requirement. | Fail | Ankit | 2019-11-14 | Caption : Short Name--Placeholder : --- | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_008 | TP_dKosh_General_SMF1_001 | 8 | Web, Mobile | General | Create Form | M | Ankit | Validation |  | Verify, Short Name field data validation (Min and Max length) | 1. Go to manage form list. 2. Click on plus icon. 3. Enter data in the Short Name field. | db length should be 25. |  | Not validation for max length. It should accept only 25 character. | Fail | Ankit | 2019-11-14 | Not defined message in requirement sheet. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_011 | TP_dKosh_General_SMF1_001 | 11 | Web, Mobile | General | Create Form | M | Ankit | UI |  | Verify, Caption, Placeholder, Control type and default value of 'Response Table Name' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Check Response Table Name | Caption : Response Table Name Place Holder : -- Control Type : -- Default Value : -- |  | Not displaying a label | Fail | Ankit | 2019-11-14 | Display label. | Resolve |  | Pass | Jaikishan (3 Dec)
TCA_dKosh_General_SMF1_001_013 | TP_dKosh_General_SMF1_001 | 13 | Web, Mobile | General | Create Form | A | Jaikishan | Validation |  | Verify, 'Response Table Name' field data validation (Min & Max Length) | 1. Go to manage form list. 2. Click on plus icon. 3. Fill Short Name. | Db length should be 50. |  | There is not a functionalilty. | Fail | Ankit | 2019-11-15 | Length can be 25 characters. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_014 | TP_dKosh_General_SMF1_001 | 14 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of Available From field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Available From' field. | Caption : Available From Place Holder : None Control Type : Datepicker Default Value : None |  | Previous date is not accepting | Fail | Ankit | 2019-11-15 | Defined new message.--Previous date is accepting. | Resolve |  | Fail | Jaikishan (3 Dec) | Previous date not accepted on Web
TCM_dKosh_General_SMF1_001_015 | TP_dKosh_General_SMF1_001 | 15 | Web, Mobile | General | Create Form | M | Jaikishan | Validation |  | Verify, 'Available From' field data validation is mandatory. | 1. Go to manage form list. 2. Click on plus icon. 3. Select Other field excluing 'Available From" | "Available From" field should be mandatory. |  | Field is optional | Fail | Ankit | 2019-11-15 | "Available From" field can be mandatory. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_018 | TP_dKosh_General_SMF1_001 | 18 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Available Upto' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Available Upto' field. | Caption : Availbale Upto Place Holder : None Control Type : Datepicker Default Value : None |  | Different caption and place holder is not defined in requirement. | Fail | Ankit | 2019-11-15 |  | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_022 | TP_dKosh_General_SMF1_001 | 22 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Allowed Duration' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Allowed Duration' field. | Caption : Allowed Duration Place Holder : -- Control Type : Text (Autocomplete) Default Value : 0 (means no limit) |  | Control type should be text or Requirement sheet. | Fail | Ankit | 2019-11-15 |  | Resolve |  | Pass | Jaikishan (3 Dec)
TCA_dKosh_General_SMF1_001_025 | TP_dKosh_General_SMF1_001 | 25 | Web, Mobile | General | Create Form | A | Aditya | Validation |  | Verify, 'Allowed Duration' field data validation. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Allowed Duration' field. | 1. Count from 0 to 11 for HH (hours) 2. Count from 0 to 59 for MM (Minutes) | Requirement sheet is wrong for Hour maximum value. | Hour accept upto 11 and minute 59. | Fail | Ankit | 2019-11-15 | Acepting negative values | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_026 | TP_dKosh_General_SMF1_001 | 26 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of Response Frequency field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on Response Frequency field. | Caption : Response Frequency Place Holder : -- Control Type : Dropdown Default Value : None |  | Default value should be displayed as Once | Fail | Ankit | 2019-11-14 | There is no any default value. | Resolve |  | Pass | Jaikishan (3 Dec) | No default value on web also.
TCA_dKosh_General_SMF1_001_028 | TP_dKosh_General_SMF1_001 | 28 | Web, Mobile | General | Create Form | A | Aditya | Validation |  | Verify, Value selection in Response Frequency dropdown is mandatory. | 1. Go to manage form list. 2. Click on plus icon. 3. Fill all requied info excluding Response Frequency. | -Field should be mandatory. -There should be shown error message 'Please select Response frequency' |  | Not mandatory | Fail | Ankit | 2019-11-15 | it is mandatory. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_029 | TP_dKosh_General_SMF1_001 | 29 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Shuffle questions?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Shuffle questions?' field. | Caption: Shuffle questions? Place Holder: -- Control Type : Toggle Default Value : 0 i.e. No |  | Caption is different | Fail | Ankit | 2019-11-15 | Same caption. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_031 | TP_dKosh_General_SMF1_001 | 31 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Link to another app?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Link to another app?' field. | Caption : Link to another app? Place Holder : -- Control Type : Switch Default Value : 0 i.e. No |  | Caption is different | Fail | Ankit | 2019-11-15 | Caption is same. | Resolve |  | pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_033 | TP_dKosh_General_SMF1_001 | 33 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Negative marking?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Negative marking?' field. | Caption : Negative marking? Place Holder : -- Control Type : Toggle Default Value : No |  | Caption is not matching | Fail | Ankit | 2019-11-15 | Caption is match. | Resolve |  | Pass | Jaikishan (3 Dec)
TCM_dKosh_General_SMF1_001_033 | TP_dKosh_General_SMF1_001 | 33 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'In Percent? ' and 'In Number?' field. | 1. Go to manage form list. 2. Click on plus icon. | Caption : In Percent? and In Number? Place Holder : -- Control Type : Radio button Default Value : No |  | Radio Button caption is not matching. | Fail | Ankit | 2019-11-15 | Caption is not matching'. | Resolve |  | Pass | Jaikishan (3 Dec)
TCA_dKosh_General_SMF1_001_039 | TP_dKosh_General_SMF1_001 | 39 | Web, Mobile | General | Create Form | A | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Can responses be modified?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Can responses be modified?' field. | Caption: Can responses be modified? Place Holder: -- Control Type : Toggle Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 | Caption is same. | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_041 | TP_dKosh_General_SMF1_001 | 41 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Is response verification required ?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Is response verification required ?' field. | Control Type : Switch Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 | Caption is same. | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_043 | TP_dKosh_General_SMF1_001 | 43 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Is response approval required ?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Is response approval required ?' field. | Control Type : Switch Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 | Caption is same. | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_045 | TP_dKosh_General_SMF1_001 | 45 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Notify owner on response submission?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on ''Notify owner on response submission? field. | Control Type : Switch Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 | Caption is same. | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_047 | TP_dKosh_General_SMF1_001 | 47 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Notify approver on response submission?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Notify approver on response submission?' field. | Caption : Notify approver on response submission? Place Holder : -- Control Type : Toggle Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 |  | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_049 | TP_dKosh_General_SMF1_001 | 49 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Notify respondent on response submission?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Notify respondent on response submission? field. | Control Type : Switch Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 |  | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_051 | TP_dKosh_General_SMF1_001 | 51 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Notify respondent on response approval?' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Click on 'Notify respondent on response approval?' field. | Control Type : Switch Default Value : 0 i.e. No |  | Caption is different (Space before question mark) | Fail | Ankit | 2019-11-15 | Caption is different. | Resolve |  | Pass | Jaikishan (3 Dec) | Same in requirement sheet, no space
TCM_dKosh_General_SMF1_001_053 | TP_dKosh_General_SMF1_001 | 53 | Web, Mobile | General | Create Form | M | Aditya | UI |  | Verify, Caption, Place holder, Control type and default value of 'Instruction' field. | 1. Go to manage form list. 2. Click on plus icon. 3. Fill required info and save. 4. Go to setting page. | Control Type : Textarea Default Value : -- |  |  | Fail | Ankit | 2019-11-15 |  |  | Resolve | Pass | Jaikishan (3 Dec)
TCA_dKosh_General_SMF1_001_054 | TP_dKosh_General_SMF1_001 | 54 | Web, Mobile | General | Create Form | A | Aditya | Validation |  | Verify, 'Instruction' field data validation. | 1. Go to manage form list. 2. Click on plus icon. 3. Fill required info and save. 4. Go to setting page. 5. Verify, 'Status' field data validation. | Max length(db) is 1000 (varchar). | Lorem Ipsum is simply dummy text of the printing and typesetting industry. Lorem Ipsum has been the industry's standard dummy text ever since the 1500s, when an unknown printer took a galley of type and scrambled it to make a type specimen book. It has survived not only five centuries, but also the leap into electronic typesetting, remaining essentially unchanged. It was popularised in the 1960s with the release of Letraset sheets containing Lorem Ipsum passages, and more recently with desktop publishing softwa There are many variations of passages of Lorem Ipsum available, but the majority have suffered alteration in some form, by injected humour, or randomised words which don't look even slightly believable. If you are going to use a passage of Lorem Ipsum, you need to be sure there isn't anything embarrassing hidden in the middle of text. All the Lorem Ipsum generators on the Internet tend to repeat predefined chunks as necessary, making this the first true generator on the Internet. | - Accepting more than 1000 character. - On save, message is displaying insertion fail. | Fail | Ankit | 2019-11-18
TCM_dKosh_General_SMF1_002_058 | TP_dKosh_General_SMF1_002 | 58 | Web, Mobile | General | Create Form | M | Aditya | Functional |  | Verify, post action after switch on of 'Link to another app'. | 1. Go to manage form list. 2. Click on plus icon. 3. Switch on of 'Link to another app'. | Respondent can not directly open this form from dKOSH, it will be open through dependent app(Linked app). |  | With Same name it is accepting. | Fail |  | 2019-11-27 | It can acept with same name and date of created form is also show wrong on manage form page. | Resolve |  | Pass | Jaikishan (3 Dec)
[14 empty] | - Available from and Upto data is saving wrong. Time is saving 12:00:00 - In tbl_sf_form_log - empty string is saving in dat_available_upto column. If there is no data then default value (null) should be saved. | Fail
[14 empty] | Not checking this validation | Fail | Ankit | 2019-11-14 | Ankit

## Failed TCs - Response View(M)
Test Case ID | Test Plan ID | TC # | Platform | Sub Module Features | Action | Test Mode | Created By | Test Case Type | Pre Condition | Test Case Description | Steps | Expected Result | Conditions / Formula / Query | Actual Result | Pass/Fail | Executed By | Date Execution | Remarks
TCM_dKosh_General_SMF1_034_076 | TP_dKosh_General_SMF1_034 | 76 |  | Form View |  | M | Ankit | UI | Form is created for Responses | Verify the type of question is displaying same as if question type is File. |  | Same type of question should be display |  |  | Fail
TCM_dKosh_General_SMF1_034_077 | TP_dKosh_General_SMF1_034 | 77 |  | Form View |  | M | Ankit | UI | Form is created for Responses | Verify the type of question is displaying same as if question type is Scale. |  | Same type of question should be display |  |  | Fail
TCM_dKosh_General_SMF1_034_079 | TP_dKosh_General_SMF1_034 | 79 |  | Form View |  | M | Ankit | UI | Form is created for Responses | Verify the type of question is displaying same as if question type is Time. |  | Same type of question should be display |  | Short text is displaying | Fail
TCM_dKosh_General_SMF1_034_093 | TP_dKosh_General_SMF1_034 | 93 |  | Form View |  | M | Ankit | Validation | Form is created for Responses | Verify the prefill value is displaying same as if question type is Email. |  | Prefill value should be show in that field |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_094 | TP_dKosh_General_SMF1_034 | 94 |  | Form View |  | M | Ankit | Validation | Form is created for Responses | Verify the prefill value is displaying same as if question type is Number. |  | Prefill value should be show in that field |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_095 | TP_dKosh_General_SMF1_034 | 95 |  | Form View |  | M | Ankit | Validation | Form is created for Responses | Verify the prefill value is displaying same as if question type is URL. |  | Prefill value should be show in that field |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_096 | TP_dKosh_General_SMF1_034 | 96 |  | Form View |  | M | Ankit | Validation | Form is created for Responses | Verify the prefill value is displaying same as if question type is AutoComplete. |  | Prefill value should be show in that field |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_097 | TP_dKosh_General_SMF1_034 | 97 |  | Form View |  | M | Ankit | UI |  | Verify the Question is displaying correctly for question type. |  |  |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_098 | TP_dKosh_General_SMF1_034 | 98 |  | Form View |  | M | Ankit | UI |  | Verify the Options are displaying correctly if question type is Multiple Choice and choice source type is User Defined List. |  | Options should be displayed as given in question |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_103 | TP_dKosh_General_SMF1_034 | 103 |  | Form View |  | M | Ankit | UI |  | Verify the Options are shuffling if Suffle Choice is Yes if question type is Checkbox and choice source type is User Defined List. |  |  |  | Value is not displaying | Fail
TCM_dKosh_General_SMF1_034_109 | TP_dKosh_General_SMF1_034 | 109 |  | Form View |  | M | Ankit | UI |  | Verify the Option is not displaying if option is deleted in question if question type is Autocomplete and choice source type is User Defined List. |  | Deleted Option should not be show in Response/Preview Form |  | Not shuffle the choices | Fail
TCM_dKosh_General_SMF1_034_110 | TP_dKosh_General_SMF1_034 | 110 |  | Form View |  | M | Ankit | UI |  | Verify the displaying order of Option in form View if Shuffe Choice is NO and question type is Multiple Choice and choice source type is User Defined List. |  | Option should be displayed according to Question's ordering. |  | Not shuffle the choices | Fail
TCM_dKosh_General_SMF1_034_111 | TP_dKosh_General_SMF1_034 | 111 |  | Form View |  | M | Ankit | UI |  | Verify the displaying order of Option in form View if Shuffe Choice is NO and question type is Checkbox and choice source type is User Defined List. |  | Option should be displayed according to Question's ordering. |  | Not shuffle the choices | Fail
TCM_dKosh_General_SMF1_034_112 | TP_dKosh_General_SMF1_034 | 112 |  | Form View |  | M | Ankit | UI |  | Verify the displaying order of Option in form View if Shuffe Choice is NO and question type is Dropdown and choice source type is User Defined List. |  | Option should be displayed according to Question's ordering. |  | Not shuffle the choices | Fail

## Failed TCs -Section Mgmt
Test Case ID | Test Plan ID | TC # | Platform | Sub Module Features | Action | Test Mode | Created By | Test Case Type | Pre Condition | Test Case Description | Steps | Expected Result | Conditions / Formula / Query | Actual Result | Pass/Fail | Executed By | Date Execution | Remarks | Developer Status | Developer Remark
TCM_dKosh_General_SMF1_009_002 | TP_dKosh_General_SMF1_009 | 2 | Web, Mobile | General | Add Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, By default 1 section is to displayed when go to "Modify Form". | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Check By default section | 1 Section is to be created by default with Name as "Section 1" |  | Section is created but with default name "Default" Should display Untitled Section | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_009_004 | TP_dKosh_General_SMF1_009 | 4 | Web, Mobile | General | Add Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Section Name' field data validation (Integer, String, Alpanumeric) | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Enter data in Section name field | Section name accept all characters. | DataType - Varchar |  | Fail | Sanjay |  |  | Resolve
TCA_dKosh_General_SMF1_009_006 | TP_dKosh_General_SMF1_009 | 6 | Web, Mobile | General | Add Section | A | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Section Name' is required. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Fill data except Section name field and Save | Not mandatory in requirement |  |  | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_009_007 | TP_dKosh_General_SMF1_009 | 7 | Web, Mobile | General | Add Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, Caption, Placeholder, Control type and default value of 'Sequence' field. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" | Caption : Sequence Place Holder : -- Control Type : Textbox Default Value : -- |  | No sequence field is given | Fail | Sanjay |  |  | Resolve | Sequence' field is available in requirment sheet.
TCM_dKosh_General_SMF1_009_008 | TP_dKosh_General_SMF1_009 | 8 | Web, Mobile | General | Add Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Sequence' field data validation (Integer, String, Alpanumeric) | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Enter data in Sequence field | There should be shown error message like 'Please enter positive integer number only' | DataType - Integer | No sequence field is given | Fail | Sanjay |  |  | Resolve | Sequence' field is available in requirment sheet.
TCA_dKosh_General_SMF1_009_009 | TP_dKosh_General_SMF1_009 | 9 | Web, Mobile | General | Add Section | A | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Sequence' field data validation (Min and Max length) | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Enter data in Sequence field | Not given in requirement sheet. |  | No sequence field is given | Fail | Sanjay |  |  | Resolve | Sequence' field is available in requirment sheet.
TCA_dKosh_General_SMF1_009_010 | TP_dKosh_General_SMF1_009 | 10 | Web, Mobile | General | Add Section | A | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Sequence' is required. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Fill data except Sequence field and Save | Save section without any error. |  | No sequence field is given | Fail | Sanjay |  |  | Resolve | Sequence' field is available in requirment sheet.
TCM_dKosh_General_SMF1_009_011 | TP_dKosh_General_SMF1_009 | 11 | Web, Mobile | General | Add Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, Caption, Placeholder, Control type and default value of 'Shuffle Questions' field. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" | Caption : Shuffle Questions Place Holder : -- Control Type : Toggle Default Value : No |  | Caption "Shuffle question?" is given | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_009_017 | TP_dKosh_General_SMF1_009 | 17 | Web, Mobile | General | Add Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, 'Instruction' field data validation (Integer, String, Alpanumeric) | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on "Add Another Section" 5. Enter data in Instruction field | Instruction accept all characters. | DataType - Varchar |  | Fail | Sanjay |  |  | Resolve | All type of characters should be input in Instruction.
TCM_dKosh_General_SMF1_009_020 | TP_dKosh_General_SMF1_009 | 20 | Web, Mobile | General | Add Section | M | Aditya | Functional | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, Post action after clicking on 'Save' button. | 1. Open create section page. 2. Fill required info. 3. Click on 'Create' button. | 1. Section should be created with acknowledge message like 'Section has been created successfully". 2. On clicking it will save all the data in DB in tbl_sf_form_section |  | Give no acknowledge message | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_010_024 | TP_dKosh_General_SMF1_010 | 24 | Web, Mobile | General | Modify Section | M | Jaikishan | UI | 1. Form must be created. 2. Section should be created. 3. User has permission to modify section. | Verify, Row Caption displayed after clicking on section list action. | 1. Go to section list 2. Click on edit section icon. | Caption : 1. Modify Section 2. Merge Section 3. Split Section 4. Reorder Section 5. Duplicate Section 6. Section Rely on 7. Delete Section |  | Caption order is not match | Fail | Sanjay |  |  | Resolve | I have set caption as per requirment sheet section.
TCM_dKosh_General_SMF1_010_029 | TP_dKosh_General_SMF1_010 | 29 | Web, Mobile | General | Modify Section | M | Aditya | Unit | 1. Form must be created. 2. Section should be created. 3. User has permission to modify section. | Verify, Sequence of section changed as per changes done by creator in sequence. | 1. Go to section list 2. Click on edit section icon. 3. Change sequence.. 4. Click on Modify/Save button. 5. Check sequence of section in that form. | Sequence should be changed as per changes done by creator/modifier. | Change from 4 to 2 then move section in 3 | no sequence | Fail | Sanjay |  |  | Resolve | It is already working fine.
TCM_dKosh_General_SMF1_011_034 | TP_dKosh_General_SMF1_011 | 34 | Web, Mobile | General | Delete Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, Two Radio button Captions. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Delete Section 6. Check radio button caption | Caption : 1. Delete all 2. Move all questions to section: |  | "Move all question to section:" is given instead of "Move all questions to section:" | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_011_038 | TP_dKosh_General_SMF1_011 | 38 | Web, Mobile | General | Delete Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Create section'. | Verify, post action when select "Move all questions to section" radio button and without selecting any section, click on "Ok" button | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Delete Section 6. Click on "Delete all" 7. Click on "OK" button | Showing validation message when click on "Ok" button. |  | Showing no error message | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_012_045 | TP_dKosh_General_SMF1_012 | 45 | Web, Mobile | General | Merge Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Merge section'. | Verify, Title, Caption, Control type and default value of 'Merge Section' pop up field. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on merge Section | Title :Merge Section Caption : Merge this section to: Control Type : Dropdown Default Value : -- |  | In dropdown no arrow is given | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_012_051 | TP_dKosh_General_SMF1_012 | 51 | Web, Mobile | General | Merge Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Merge section'. | Verify, Questions in section is merged with another section when "Merge Section" to another section. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on merge Section 6. Select any section and "Ok" 7. Open that section and check questions of previous section | All questions should be merged with selected section. |  | Cases is generating | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_015_052 | TP_dKosh_General_SMF1_015 | 52 | Web, Mobile | General | Duplicate Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Duplicate section'. | Verify, "Duplicate Section" pop up opened. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Duplicate Section | "Duplicate Section" pop-up should be opened. With Text as "Are you sure you want to duplicate %1(section name)? | Duplicate section requirement sheet is not present | Pop-up is not open duplicate section direct created | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_015_053 | TP_dKosh_General_SMF1_015 | 53 | Web, Mobile | General | Duplicate Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Duplicate section'. | Verify, buttons when click on "Duplicate Section". | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Duplicate Section | Ok and Cancel button should be show |  | No pop-up open | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_014_062 | TP_dKosh_General_SMF1_014 | 62 | Web, Mobile | General | Reorder Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Reorder section'. | Verify, Drag section in Reorder section list | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Reorder Section 6. Drag section | Section should be move when drag section from one place to another. |  | No drag functionality is given | Fail | Sanjay |  |  | Hold | Hold for next version
TCM _dKosh_General_SMF1_014_063 | TP_dKosh_General_SMF1_014 | 63 | Web, Mobile | General | Reorder Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Reorder section'. | Verfiy, Sequence number when we reorder section. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Reorder Section 6. Drag section | Section sequence number change according to the list. |  | No drag functionality is given | Fail | Sanjay |  |  | Hold | Hold for next version
TCM _dKosh_General_SMF1_014_065 | TP_dKosh_General_SMF1_014 | 65 | Web, Mobile | General | Reorder Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Reorder section'. | Verify, Section sequence number changed when reorder section. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Reorder Section 6. Drag section 7. Click on "Ok" button 8. Open any section 9. Check sequence number. | Sequence number should be changed section form. |  | No drag functionality is given | Fail | Sanjay |  |  | Hold | Hold for next version
TCM _dKosh_General_SMF1_013_068 | TP_dKosh_General_SMF1_013 | 68 | Web, Mobile | General | Split Section | M | Jaikishan | UI | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, all labels,Checkbox,Radio button in Split section pop-up | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section | Heading : Select Questions to move Side heading : Total Questions (selected questions count) Checkbox : Select all & All Quesion checkbox Move <selected question count> questions to: Radio button : New Section, Existing Section |  | In Heading "Select Question to move" is given. Move <selected question count> questions to:In this <selected question count> is not given | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_070 | TP_dKosh_General_SMF1_013 | 70 | Web, Mobile | General | Split Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Split section'. | Verfiy, Selected Question number changes when select questions checkbox. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section 6. Select question checkbox one by one. 7. Click on "Ok" button. | 1. Selected Question number changes accordingly. 2. Move <question number> changes accordingly |  | Move <question number> is not changes accordingly | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_071 | TP_dKosh_General_SMF1_013 | 71 | Web, Mobile | General | Split Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, all questions in the section displayed on list. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section. | 1. All Question showing in the list. 2. Questions shortname is displaying |  | Question is showing instead of short name | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_072 | TP_dKosh_General_SMF1_013 | 72 | Web, Mobile | General | Split Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, "Ok" button when only checkbox selected & radio button not selected. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section 6. Select any question checkbox 7. Click on "Ok" button. | Radio button should be mandatory when question checkbox is selected. |  | Radio button is not given mandatory when question checkbox is selected. | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_073 | TP_dKosh_General_SMF1_013 | 73 | Web, Mobile | General | Split Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, "Ok" button when no checkbox selected & radio button selected. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section 6. Select any radio button 7. Click on "Ok" button. | "Please select alleast 1 question " message should be show |  | "Please select question for split" given instead of "Please select alleast 1 question" | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_075 | TP_dKosh_General_SMF1_013 | 75 | Web, Mobile | General | Split Section | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, post action when select question and Existing Section(Radio button). | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section 6. Select questions 6. Select Existing section radio button 7. Click on "Ok" button. | 1. Existing section dropdown should be visible with all section in the form showing except Split section name. 2. Message "Please select an item in the list." should be show. |  | Message "Please select section" is showing instead of "Please select an item in the list." | Fail | Sanjay |  |  | Resolve
TCM _dKosh_General_SMF1_013_078 | TP_dKosh_General_SMF1_013 | 78 | Web, Mobile | General | Split Section | M | Jaikishan | Validation | 1. Form must be created. 2. User has permission of 'Split section'. | Verify, On "Ok" message when select question and select new section/Existing section. | 1. Go to manage form list. 2. Click on List Action. 3. Click on "Modify Form" 4. Click on section action. 5. Click on Split Section 6. Select questions 6. Select new section radio button 7. Click on "Ok" button. | Message "Saved Successfully" should be show. |  | Message "Saved Successfully" is not showing. | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_084 | TP_dKosh_General_SMF1_016 | 84 | Web, Mobile | Section Rely on | Create | M | Jaikishan | UI |  | Verify the Caption, Place holder of table. | 1. Go to manage form list. 2. Click on Modify form in Action. 3. Click on section list in action. 4. Click on link. 5. Verify table caption | Caption: Select question and response to display above section. |  | No Caption is given for table | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_085 | TP_dKosh_General_SMF1_016 | 85 | Web, Mobile | Section Rely on | Create | M | Jaikishan | UI | i | Verify the Caption and fields of the Depends on Section table. | 1. Go to manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Verify the caption. | There should be shown with default two rows three columns in table. Row 1 - Caption: Section, Question, Response and + button Row 2 - Section Dropdown, Question Dropdown, Response multiselect field, Delete icon |  | Table structure is different | Fail | Sanjay |  |  | Resolve | We have to change table structure of Section Depends on as per mobile screen.
TCM_dKosh_General_SMF1_016_088 | TP_dKosh_General_SMF1_016 | 88 | Web, Mobile | Section Rely on | Create | M | Jaikishan | Functional |  | Verify the data in Section dropdown. | 1. Go to Manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Verify the data of Section dropdown. | All section which are define in modify form list except current section. | All sections which are define current and before this question's section. | Current section is also showing | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_093 | TP_dKosh_General_SMF1_016 | 93 | Web, Mobile | Section Rely on | Create | M | Jaikishan | Functional |  | Verify that error message is displaying after click on Save button, if user is not selecting the Section Rely on field data. | 1. Go to Manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Don't select the data in section field. 6. Click on Ok button | "Please select dependency for section" message should be displayed. |  | No error message show | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_094 | TP_dKosh_General_SMF1_016 | 94 | Web, Mobile | Section Rely on | Create | M | Jaikishan | Functional |  | Verify that error message is displaying after click on Save button if user not fill data for Question field. | 1. Go to Manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Select the data in Section field. 6. Don't fill the data in Question field 7. Click on Ok button | Error message should be displayed. |  | No error message show | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_095 | TP_dKosh_General_SMF1_016 | 95 | Web, Mobile | Section Rely on | Create | M | Jaikishan | Functional |  | Verify that error message is displaying after click on Save button if user not fill data for Choice field. | 1. Go to Manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Select the data in Section field. 6. Select the data in Question field. 7. Don't fill the data in Choices field 8. Click on Ok button | Error message should be displayed. |  | No error message show | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_016_099 | TP_dKosh_General_SMF1_016 | 99 | Web, Mobile | Section Rely on | Modify | M | Jaikishan | Functional |  | Verify the confirmation message is asked before deleting the data. | 1. Go to Manage form list. 2. Click on Modify form in Action. 3. Click on section list in action.. 4. Click on Section Rely on. 5. Delete the data 6. Save the form. | Some confimation message should be asked before delete. |  | No Confirmation message is asked before deleting | Fail | Sanjay |  |  | Resolve
TCM_dKosh_General_SMF1_036_134 | TP_dKosh_General_SMF1_036 | 134 | Web, Mobile | Master Question bank |  | M | Jaikishan | Database |  | Verify the Size of columns in tbl_sf_master_question table with ERP database sheet. | 1. Open database 2. Verify values | All values should be matched |  | txt_choice_lov_query, type and size not matched | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan
TCM_dKosh_General_SMF1_036_137 | TP_dKosh_General_SMF1_036 | 137 | Web, Mobile | Master Question bank | Export to Question Bank | M | Jaikishan | UI |  | Verify, label,Sequence,Hover of "Export to question bank" at Question level. | 1. Create Form 2. Create some question on it. 3. Click on question action. 4. Check label of Export | Label : Export To Question Bank Sequence : ? Hover : Export To Question Bank |  | Showing "Export Question" | ? | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_138 | TP_dKosh_General_SMF1_036 | 138 | Web, Mobile | Master Question bank | Export to Question Bank | M | Jaikishan | Validation |  | Verify, Confirmation pop up when click on "Export to question bank". | 1. Click on Question action. 2. Click on "Export to question bank" 3. Check pop up. | Confirmation Message "Are you sure, you want to Export shortname_1 to question bank? |  | No confirmation message showing. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_139 | TP_dKosh_General_SMF1_036 | 139 | Web, Mobile | Master Question bank | Export to Question Bank | M | Jaikishan | Validation |  | Verify, Message after click on "Ok" button of confirmation pop up. | 1. Click on Question action. 2. Click on "Export to question bank" 3. Click on "Ok" button | On click message should be "Question has been exported successfully." |  | Message "Question has been export successfully." is showing. Add 'ed' in export. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_140 | TP_dKosh_General_SMF1_036 | 140 | Web, Mobile | Master Question bank | Export to Question Bank | M | Jaikishan | Validation |  | Verify, Confirmation pop up after click on "Cancel" button of confirmation pop up. | 1. Click on Question action. 2. Click on "Export to question bank" 3. Click on "Cancel" button | Confirmation pop up should be close. |  | No showing any pop up | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_143 | TP_dKosh_General_SMF1_036 | 143 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | UI |  | Verify, label,Sequence,Hover of "Export Questions" at Section level. | 1. Create Form 2. Create some question on it. 3. Click on Section action. 4. Check label of Export | Label : Export Questions Sequence : ? Hover : Export Questions |  | Showing "Export question", Q should be capital, and add 's' in Question. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_144 | TP_dKosh_General_SMF1_036 | 144 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | UI |  | Verify, Export Question pop up & Heading when click on "Export Questions" link. | 1. Click on Export Questions 2. Check pop up | Export Question pop up should be open. Heading : Export Questions |  | Heading not showing. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_145 | TP_dKosh_General_SMF1_036 | 145 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | UI |  | Verify, Label in Export Question pop up. |  | Select 'Section name' questions to export 7 Questions (0 selected) |  | Not matched with expected. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Reopen
TCM_dKosh_General_SMF1_036_146 | TP_dKosh_General_SMF1_036 | 146 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | Validation |  | Verify, already exported question not show in list. | 1. Export one question from question level. 2. Click on Section list action 3. Click on Export Questions 4. Check that question in list. | Already exported question should not be showing in list. |  | Already exported question showing in list. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_151 | TP_dKosh_General_SMF1_036 | 151 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | Validation |  | Verify, "Ok" button when there is no question in the section. | 1. Click on Section list action 2. Click on Export Questions 3. Click on "OK" button | Showing : 1. No result Found in list. 2. On Click "Ok" back to modify form. |  | Not showing no result found. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_152 | TP_dKosh_General_SMF1_036 | 152 | Web, Mobile | Master Question bank | Export Questions | M | Jaikishan | UI |  | Verfiy, Question UI on export question list. |  | 1. Question_short_name Question Type :1 option 2. Question_short_name Question Type | 1. job_description Drop Down: 2 options | 1. Extra space between 1. and shortname. 2. Question type not just below of shortname. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_154 | TP_dKosh_General_SMF1_036 | 154 | Web, Mobile | Master Question bank | Import Questions | M | Jaikishan | UI |  | Verify, label,Sequence,Hover of "Import Questions" at Section level | 1. Create Form 2. Create some question on it. 3. Click on section action. 4. Check label of Import | Label : Import Questions Sequence : ? Hover : Import Questions |  | Question 'q' should be capital. & add 's' in question. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_155 | TP_dKosh_General_SMF1_036 | 155 | Web, Mobile | Master Question bank | Import Questions | M | Jaikishan | UI |  | Verify, Import Question pop up & Heading when click on "Import Questions" link. | 1. Click on Import Questions 2. Check pop up | Import Question pop up should be open. Heading : Import Questions |  | Heading not showing. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_156 | TP_dKosh_General_SMF1_036 | 156 | Web, Mobile | Master Question bank | Import Questions | M | Jaikishan | UI |  | Verify, Options in Import Questions pop up. | 1. Click on Import Questions 2. Check pop up | Options are : 1. Import from another form 2. Import from question bank |  | Option label not matched. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_159 | TP_dKosh_General_SMF1_036 | 159 | Web, Mobile | Master Question bank | Import Questions | M | Jaikishan | Validation |  | Verify, Form drodown in "Import from another form" | 1. Click on Import Questions 2. Click on Import from another form. 3. Check form dropdown list. | All form Name should be displayed in dropdown list. | New status form also showing????? | 1. Form shortname displaying instead of form name. 2. All form displayed, whether it is shared or in any status. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed
TCM_dKosh_General_SMF1_036_161 | TP_dKosh_General_SMF1_036 | 161 | Web, Mobile | Master Question bank | Import Questions | M | Jaikishan | Intergration |  | Verify, which form showing in form dropdown list?? |  | 1. Form which is created by owner should show in list, Except form status New,Closed. 2. Share Form with Edit permission should show in list. 3. Share Form with Analyse permission should not show. |  | 1. New status form also showing in list. 2. Share form with analyse permission showing in list. | Fail | Jaikishan | 2019-12-27 | TR2019W52 - Jaikishan | Resolved |  | Closed

## Failed TCs -Manage Form(Mbl)
Test Case Id | Test Plan Id | TC # | Platform | Sub Module Features | Action | Test Mode | Created By | Test Case Type | Pre Condition | Test Case Description | Steps | Expected Result | Actual Result | Pass/Fail | Executed By | Date Execution | Remarks | Retesting (Pass/Fail) | Developer Status | Developer Remark
TCM_dKosh_General_SMF1_022_008 | TP_dKosh_General_SMF1_022 | 8 |  | General | Manage Form List | M | Aditya | Functional | 1. Form must be created. 2. User has permission of 'View form List'. | Verify, Search is working on list of Form. | 1. Go to 'Manage Form' list. 2. Search records(forms) by Name,Short name,Owner, Status. | Searched records should be displayed in list. | Search working on form name only. | Fail | Omkar |  |  |  | Resolve | Search engine onlu working on form name as per mobile UI ,which are shared by mohit sir.
TCM_dKosh_General_SMF1_022_010 | TP_dKosh_General_SMF1_022 | 10 |  | General | Manage Form List | M | Aditya | Functional | 1. Form must be created. 2. User has permission of 'View form List'. | Verify, displaying order(default) of forms in list. | 1. Go to 'Manage Form' list. 2. Search records(forms) by Name,Sort name,Owner/Date,Sections/Questions and Status. | Form should be show according to last in last show in list. | Search functionality can working on form name only. | Fail | Omkar |  |  |  | Resolve
TCM_dKosh_General_SMF1_003_014 | TP_dKosh_General_SMF1_003 | 14 |  | General | Manage Form List | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'View form List'. | Verify, post action for "Accept Responses" when form status is in different status | 1. Go to 'Manage Form' list. 2. Check active responses button for different status of form | 1. Final status - Active response toggle can be changed to "Yes". 2. Inactive status - Active response toggle can be changed to "Yes". 3. OnHold status - Active response toggle can be changed to "Yes". 4. New/Close status - Active response toggle cannot be changed to "Yes". | There is an link for active responses. | Fail | Omkar |  |  | Fail | Resolve
TCM_dKosh_General_SMF1_028_026 | TP_dKosh_General_SMF1_028 | 26 |  | General | Manage Form -Action | M | Aditya | Functional | 1. Creator/Modifier has permission to modify form. 2. Form should be editable(as per document status). 3. Status of form is 'New'. | Verify, post action when user select 'Settings'. | 1. Go to manage form list. 2. Click on Action icon. 3. Select 'Settings' | It will redirect to modify page | Not redirect to forms result page.And shows error also onclick. | Fail | Omkar |  |  | Fail
TCM_dKosh_General_SMF1_028_027 | TP_dKosh_General_SMF1_028 | 27 |  | General | Manage Form -Action | M | Jaikishan | Functional | 1. Creator/Modifier has permission to modify form. 2. Form should be editable(as per document status). 3. Status of form is 'New'. | Verify, post action when user select 'Delete'. | 1. Go to manage form list. 2. Click on Action icon. 3. Select 'Delete' | Delete Form Pop-up should be open. | There is no icon of delete test responses. | Fail | Omkar |  |  | Fail | Resolve | No need of Delete Test Responses on Mobile side as per discussion with Naveen Yadav sir,
[13 empty] | There is no pop open for closed status. | Fail | Omkart |  |  | Fail

## Failed TCs - Create Question(Mb
Actual Result | Pass/Fail | Executed By | Date Execution | Remarks | Developer Status | Developer Remark
For txt_error_length_msg - NUL is displaying | Fail | Ankit | 2019-11-27 |  | Resolve
Primary key is not set | Fail | Ankit | 2019-11-27 |  | Resolve
| Fail | Ankit | 2019-11-27 |  | Resolve | Need discussion.
| Fail | Ankit | 2019-11-27 |  | Resolve
| ? | Ankit | 2019-11-27 |  | Resolve | It should be mandatory
Not tested | ? | Jaikishan | 2019-11-29 |  | Resolve
Not mandatory, save without any error | Fail | Jaikishan | 2019-11-29 |  | Resolve
Different from web(in Web only accept character,underscore) | Fail | Jaikishan | 2019-11-29 |  | Resolve | Short name should be accept small alphabet, number and _ values.
Accept more than 50 length | Fail | Jaikishan | 2019-11-29 |  | Resolve
In sheet it is written as Text with 100 character. | ? | Jaikishan | 2019-11-30 |  | Resolve
Select source type should be mandatory | Fail | Jaikishan | 2019-11-30 |  | Resolve
Placeholder should be Select Choice Source Type | Fail | Jaikishan | 2019-11-30 |  | Resolve
Weekdays fields also showing | Fail | Jaikishan | 2019-11-30 |  | Resolve
It save with default value, not showing any error message. | Fail | Jaikishan | 2019-11-30 |  | Resolve | We have removed Choice Source type from dropdown,now user defind list choice will be selected by default.
Title not macthed , showing "Manage Query" | Fail | Jaikishan | 2019-11-29 |  | Resolve
Save blank value when save | Fail | Jaikishan | 2019-11-29 |  | Resolve
Serial number not displaying | Fail | Jaikishan | 2019-11-29 |  | Resolve
Image not added | Fail | Jaikishan | 2019-11-29 |  | Hold | Hold for next version on mobile side.
Shuffle choices field is missing | Fail | Jaikishan | 2019-11-29 |  | Reslove
Sequence of question doesnot change. | Fail | Jaikishan | 2019-11-29
View Result functionality not working | Fail | Jaikishan | 2019-11-29
Functionality not working | Fail | Jaikishan | 2019-11-29 |  | Hold | Hold for next version on both side(Web and mobile app).
When we enter data other then numbers then it shows message in popup.Unfortunately,Dkosh has stopped. | Fail | Omkar | 2019-11-29 |  | Resolve
there is no any default value. | Fail | Omkar | 2019-11-29 |  | Resolve
Extra Minimum length and maximum length showing | Fail | Jaikishan | 2019-11-29 |  | Resolve | Yes,it is required in Question Type Information sheet.
Minimum length and maximum length field also showing | Fail | Jaikishan | 2019-11-29 |  | Resolve
Value "v" should be small Maximum value placeholder is wrong | Fail | Jaikishan | 2019-11-29 |  | Resolve | It should be capital characher.
Not showing same as expected. {Regular expression and error message field is extra} And Regular expression take data automatically. | Fail | Jaikishan | 2019-11-29 | Regular expression previous data is showing | Resolve
User can not edit allowed extension successfully | Fail |  |  |  | Resolve
Caption : "v" should be small | Fail |  |  |  | Resolve
Previous data showing for new question type. | Fail |  |  |  | Resolve
Accept all character,decimal value. | Fail |  |  |  | Resolve | It should be accept all type of characters.
Not showing | Fail |  |  |  | Resolve
All section displaying in section dropdown | Fail |  |  |  | Resolve

## Failed TCs- Share Form(Mbl)
Test Case Id | Test Plan Id | TC # | Platform | Sub Module Features | Action | Test Mode | Created By | Test Case Type | Pre Condition | Test Case Description | Steps | Expected Result | Conditions / Formula / Query | Actual Result | Pass/Fail | Executed By | Date Execution | Remarks | Developer Status | Developer Remark
TCJaikishan_dKosh_General_SMF1_008_012 | TP_dKosh_General_SMF1_008 | 12 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action after selecting user. | 1. Go to manage form list. 2. Click on action icon of any form. 3. Click on 'Share Form'. 4. Click on User dropdown. 5. Select any user. | After selecting user, display user name below User field. |  | Display inside the user field | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_016 | TP_dKosh_General_SMF1_008 | 16 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action after selecting 'User' in 'Can analyse' permission. | 1. Go to manage form list. 2. Click on action icon of any form. 3. Click on 'Share Form'. 4. Select any user 4. Click on 'Can analyse' dropdown 5. Click on "Ok". | 1. Select User should be able to analyse form. 2. Cannot change form status 3. Not change accept responses toggle. |  | Can analyse functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_019 | TP_dKosh_General_SMF1_008 | 19 |  | Share Form | Share Form | M | Jaikishan |  | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, Only one owner should be show for one form. | 1. Go to manage form list. 2. Click on action icon of any form. 3. Click on 'Share Form'. 4. Select any user & Save. 5. change user permission to "Is owner" 6. Click on "ok" | Only one owner should be show for one form | . | "Is Owner" functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_022 | TP_dKosh_General_SMF1_008 | 22 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action after click on Remove user icon | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Click on remove user | 1. Remove user details from the access list. 2. Hand cursor should be showing on hover |  | Cross functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_023 | TP_dKosh_General_SMF1_008 | 23 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action after click on Remove user icon | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Click on remove user | Form should not show in user account. |  | Cross functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_025 | TP_dKosh_General_SMF1_008 | 25 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action when admin can modify permission of user from "Can Edit" to "Can analyse". | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Change user permission | User can now only analyse the form. |  | Can analyses functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_026 | TP_dKosh_General_SMF1_008 | 26 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, post action when admin can give permission of "is owner" to the user. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Change user permission | User will now become admin of the form page. | What permission remain to admin? | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_027 | TP_dKosh_General_SMF1_008 | 27 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, "Action done by User with "Can Analyse" permission of Form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. User with Can analyser permission. 5. Go to user account 6. Check action done by user. | ?? |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_028 | TP_dKosh_General_SMF1_008 | 28 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, User with "Analyse" permission can View the form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Check user can view the form. | ?? |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_029 | TP_dKosh_General_SMF1_008 | 29 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, User with "Analyse" permission can change the status of form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Change form status. | Form status should not be changed. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_030 | TP_dKosh_General_SMF1_008 | 30 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, User with "Analyse" permission can change Accept Response toggle as "Yes" or "No" | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Change accept responses. | Accept responses toggle should not be changed. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_031 | TP_dKosh_General_SMF1_008 | 31 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, User with "Analyse" permission when click on "Share form" | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Click on "Share Form" | Caption "You must ask the owner to invite the people or share form." should be shown. 2. Send Request button should be present. | How to ask to owner to share form??? | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_032 | TP_dKosh_General_SMF1_008 | 32 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, User with "Analyse" permission can view Analyse result. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Click on form list action 6. Check Analyse Result. | User can Analyse result |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_033 | TP_dKosh_General_SMF1_008 | 33 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, Owner action and User with Edit permission action same for form. |  | ?? |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_034 | TP_dKosh_General_SMF1_008 | 34 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Veriy, User with Edit permission modify the form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Modify form 6. Click on SAve. | Modified form should reflect to all user of that form. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_035 | TP_dKosh_General_SMF1_008 | 35 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Veriy, User with Edit permission Manage the Respondent of the form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Manage Respondent. 6. Click on SAve. | manage respondent should reflect to all user of that form. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_036 | TP_dKosh_General_SMF1_008 | 36 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Veriy, User with Edit permission can Delete the form. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Go to User account. 5. Delete Form 6. Click on SAve. | Form should be deleted from all shared users. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_037 | TP_dKosh_General_SMF1_008 | 37 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, Owner, when owner give "is Owner" permission to multiple users. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 4. Give "Is owner" permission to multiple users. 5. Click on "ok" button | ?? | Only one owner should be show at a time. | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_038 | TP_dKosh_General_SMF1_008 | 38 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, Multiple Owner can have a same permission. |  | 1. Multiple Owner cannot create. 2. If Create , then all owner have a same permission. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_039 | TP_dKosh_General_SMF1_008 | 39 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, owner can remove another owner. |  | 1. Multiple Owner cannot create. 2. If Create , then owner have a permission to remove another owner. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_040 | TP_dKosh_General_SMF1_008 | 40 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, "Acknowledge Message" after click on "ok" button | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 5. Click on "ok" button | Message "Saved successfully" should be showing. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_041 | TP_dKosh_General_SMF1_008 | 41 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, "Acknowledge Message" after modify permission of users. | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 5. Click on "ok" button | Message "Saved successfully" should be showing. |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_009_041 | TP_dKosh_General_SMF1_009 | 41 |  | Share Form | Share Form | M | Jaikishan | Functional |  | Verify, Ok button when no user is selected in user field | 1. Go to manage form list. 2. Click on action icon of any form with 'New' status. 3. Click on 'Share Form'. 5. Click on "ok" button | Form should not close, or error message like "Please select atleast one user" |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_008_041 | TP_dKosh_General_SMF1_008 | 41 |  | Share Form | Share Form | M | Jaikishan | Functional | 1. Form must be created. 2. User has permission of 'Share Form'. 3. Atleast one user should be mapped with that form. | Verify, user cannot open form when thier is not permission of that form | 1. Go to manage form list. 2. Click on action icon of any form 3. Click on 'Share Form'. 4. Give permission to edit 5. Then remove user from share form 6. Check user can open from link | User cannot open form from url |  | functionality is not working | Fail | Sanjay
TCJaikishan_dKosh_General_SMF1_009_041 | TP_dKosh_General_SMF1_009 | 41 |  | Share Form | Share Form | M | Jaikishan | Functional |  | Verify, User with Edit permission can change status of form. |  | Edit permission user should change the status. |  | functionality is not working | Fail | Sanjay